## Daily Status Reporting
Daily Status Report
Legend
Date |  |  | Status on track
Resource Name |  |  | Slight deviation
Reporting Manager |  |  | Not on track. Need attention
Tasks Execution Completion Status
Tasks Planned | Tasks Executed(yes/No) | Tasks Execution Status | Execution Effort(Hrs) | Complete (%) | Comments
Analysing the documents and asuming the Database tables | Yes | finished | 3 | 100
Creating basic structure of spring Application | Yes | finished | 1 | 100
Creation of entities with required fields | Yes | finished | 2 | 100
+